## Other modules
module |  |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
User | user management |  | If the Collecting Agency is selected the agency selection is mendatory? | 2024-05-20_10h11_33.mp4 | Fixed | Hasan
Agency | Agency Registration | mobile no | text is able to input | 2024-05-28_16h59_44.png | Fixed | Hasan
COA Masters | Major Group |  | 0 is able to input but not able to select with arrow | 2024-05-20_12h34_11.mp4 | Fixed | Golam |  | validation is there, they can input 0 but it wont create data
COA mapping |  |  | scheduler not working |  | New
Status Master |  | notification | This Status Name already exist or deleted! - notification displays. "This Status Name already exist" should display | 2024-05-15_16h14_12.png | Fixed | Golam |  | if someone delete a data with same name they cannot create thats why this general message is shown
User Role | Role Permission |  | need to add select all option | 2024-04-29_17h25_07.png | New
User Role |  |  | there should be select all option | 2024-05-14_16h09_19.png | New
User Role | Add Role Details | Placeholder | Select Main Menu Placeholder missing | 2024-05-14_15h52_54.png | Fixed | Hasan
User Role | Other Masters | Placeholder | New Service : Agency* | 2024-05-26_16h50_52.png | New | Hasan
Other masters | Exchange Rate | Pagination | showing up to 1 pg. though there are more data in than 10 |  | New | Hasan
Other masters | New Payment Collection Method | decimal | max 2 num should be displayed after decimal number | 2024-06-11_16h51_39.png | New | Golam
Agency | New Contact Person |  | field is not clear | 2024-06-26_15h56_25.png | Fixed | Hasan
Agency | New Contact Person |  | Date of birth is static | 2024-06-26_15h58_43.mp4 | Fixed | Hasan
Agency | New Contact Person |  | mobile no charecter |  | Fixed | Hasan
New RRCO Dzongkhag | Dzongkhag |  |  | 2024-06-26_16h05_36.mp4 | Fixed | Hasan
Agency Maintenance | Update |  | 500 error | 2024-06-26_16h43_44.png | Fixed | Hasan
User | Remove | Effective date | scheduler is not working |  | New |  | Shahin
User | Designation |  | chracter validation | 400 Error | Fixed |  | Shahin
User | Remarks |  | chracter validation | 500 Error | Fixed |  | Shahin
User management |  | Edit | remove mandatory sign | 2024-07-04_11h07_17.png | Fixed | Hasan
Configuration Option | Effective date |  | Effective date should be displayed under status - effective date | 2024-07-14_17h13_49.mp4 | Fixed | Hasan
Coa Mapping | New BTC Mapping | External System | when open BTC Mapping - ECMS is always auto selected | 2024-07-15_11h08_34.png | Fixed | Golam |  | ecms should be auto selected
Coa Mapping | New BTC Mapping | Revenue/Gl Head Name | when select gl from last page, autoatically 1st page is loaded. | 2024-07-15_11h12_23.mp4 | Fixed | Golam
Coa Mapping | New BTC Mapping |  | when only 1 in the list. by selecting all its creating | 2024-07-15_11h40_24.mp4 | need to discuss | Golam |  | Removed select all option
Coa Mapping | New BTC Mapping | search | search not working | 2024-07-15_11h46_47.mp4 | New | Golam |  | Use table arrows to go to first page, discuss further with Hasan bhai
Coa Mapping | New BTC Mapping, in every module | Commodity Checkbox | mapped gl head check-box shouldn't be able to select | 2024-07-15_12h34_08.png | Fixed | Golam |  | That feature is not implemented in btc mapping, user can only know if btc is mapped when they submit
Coa Mapping | New BTC Mapping | Checkbox | Checkbox selection issue | 2024-07-15_13h38_23.mp4 | Fixed | Golam |  | Check again if the issue is resolved
Coa Mapping | Services |  | Put mandatory sign | 2024-07-16_11h17_51.png | Fixed | Golam
Coa Mapping | Services | edit | service is able to unselect and submit without selecting any service when edit | 2024-07-16_11h28_35.mp4 | Fixed | Golam |  | That is what they asked in new requirement all service can be unselected
Coa Mapping | Services | add- list | Agency doesn't show in the list when add. but displays after reload | 2024-07-31_15h36_31.png | New |  | Shahin
Coa Mapping | Tax Type Mapping |  | Unmapped gl heads are not able to add | 2024-07-16_16h47_38.mp4 | Fixed |  | Shahin
Home page | Copy right |  | Copyright DRC should be displayed instead of 2023. or make the year dynamic | 2024-07-18_13h04_28.png | Fixed | Hasan
notification |  |  | remove (you have), number color should be green, space missing | 2024-07-25_09h35_05.png | New | Hasan
other masters | sectoral | edit- inactive | data already exits message displays, when schedule for inactive | 2024-07-26_04h03_16.mp4 | New | Hasan
other masters | sectoral | add | when add new sector instantly the second page shows. but when reload only the the 1st 10 data displays | 2024-07-26_04h17_09.mp4 | New | Hasan
other masters | Update External System | Api - 500 Error | https://birmsstagging.drc.gov.bt/api-services/core-module/api/v1/external-agency-system/13 | 2024-07-26_04h36_19.png | New | Hasan
Update not working
COA- mapping | Existing Non-Tax GST Mapping | schedular | scheduler is not working |  | New | Hasan
Transaction Type |  |  | what happens when inactive transaction? |  | Closed
Status master |  |  | what happens when Status Master? |  | Closed
Update Service | Agency* |  | 2 tabs open at a time | 2024-08-06_22h22_41.mp4 | Not a Defect
Service | add | drop down | options doesn't display properly when change it | 2024-08-11_10h18_33.mp4 | Fixed
disbursement |  |  | after disbursement point decimal chetrum show | 2024-08-11_11h20_03.png | New
Refund voucher |  |  | after disbursement point decimal chetrum show | 2024-08-11_11h23_13.png | New
Disbursement | alignment |  | Disbursement alignment | 2024-08-11_12h04_20.png | New
rfund | status |  | rfund status doesn't change after Initiate | 2024-08-11_12h08_19.png | New
2024-08-11_12h09_09.png
Unsuccessful Disbursement Treatment | remarks |  | Unsuccessful Disbursement Treatment remarks mandatory sign | 2024-08-11_12h37_09.png | Fixed
Unsuccessful Disbursement Treatment | save button |  | Unsuccessful Disbursement Treatment save button | 2024-08-11_12h39_33.mp4 | Fixed
User Create |  |  | should be - Ministry / Organization. (/) missing | 2024-08-12_11h20_59.png | Fixed
|  |  | search option space |  | New
User Create

## Write Off
module |  |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
Write Off Application | Attach Document |  | Image Document is not able to Attach | 2024-07-18_11h36_42.png | Fixed | Hasan |  | only PDF file allow
Write Off Application | Search Type |  | no word and dot missing | 2024-07-18_11h48_44.png | Fixed | Hasan
Write Off Application | Filter |  | mandatory field is not giving any notification | 2024-07-18_12h03_36.mp4 | Fixed | Hasan
Write Off Application | list | balance amount | balance is showing total amount | 2024-07-18_12h06_22.png | New | Hasan | Shahin
|  |  |  | 2024-07-18_12h07_18.png |  | Hasan
Write Off Application | breadcrum |  | Write Off Application should display | 2024-07-18_18h18_26.png | Fixed | Hasan
Write Off Application |  |  | though there's enough balance available .. still new request is not able to generate. |  | Not a Defect | Hasan |  | can b requested only once
Write Off Application |  | when select PA from list, | https://birmsstagging.drc.gov.bt/api-services/payment-service/api/v1/payment-advice/null | 2024-07-18_18h47_01.mp4 | New | Hasan
Write Off Application | Cancel, Reject |  | cancelled and rejected requests are not displayed in the write off list | 2024-07-18_18h57_56.mp4 | need to discuss | Hasan
Write Off Application | Search | TPN | data is not displayed when searching with TPN. But displays when search search with doc no | 2024-07-18_18h26_07.png | New | Hasan
|  |  |  | 2024-07-18_18h28_55.png |  | Hasan
Write Off Application | Payment Advice and Write Off Details |  | Pa Amount should be middle aligned | 2024-07-18_18h37_52.png | Fixed | Hasan

## Replenishment
module |  |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
Replenishment DRC | Add new | Receipt Voucher | Issuing Bank :, Payable Bank : Warrant Date data is not displayed in Receipt Voucher when create new Replenishment with Payment Mode Warrant | 2024-03-27_12h46_51.png | Closed | Golam
Replenishment DRC | Add new | Receipt Voucher | Issuing Bank :, Payable Bank data is not displayed date is displayed in Receipt Voucher when create new Replenishment with Payment Mode Demand Draft | 2024-03-28_02h35_20.png | Closed | Golam
Replenishment DRC | Add new | text field | text field max character validation | 2024-03-27_15h38_31.mp4 | Closed | Golam
Replenishment | Add new | text field | max character notification should be displayed | 2024-06-27_15h03_34.mp4 | Fixed | Golam |  | max 255 characters
Replenishment DRC | Replenishments | Breadcrum | Replenishment DRC should be displayed instead of Replenishments | 2024-03-27_23h31_19.png | Fixed
Replenishment DRC |  | Received Date | Received Date is not displayed as same as entered during Add | 2024-03-28_02h54_52.png | Fixed
|  |  |  | 2024-03-28_02h45_05.mp4 | Fixed
Replenishment Requests |  | Purpose : | text field max character validation | 2024-03-28_10h45_00.png | Fixed | Golam
Cancel Replenishment Request |  | Reason for Cancel |  | 2024-03-28_11h00_03.mp4 | Fixed | Golam |  | All other fields for remark and reason are validated in review and approval
Replenishment DRC | Add new | text field | text field max character validation - 500 character is able to input in evry field | 2024-04-02_12h47_22.mp4 | Not a Defect
|  |  |  | 2024-04-01_09h10_14.png | Fixed
Replenishment DRC |  | Received Date | Received Date is not displayed as same as entered during Add | 2024-04-01_03h32_23.png | Fixed
Replenishment request | edit | account type | account type is not changed after editing request | 2024-04-01_03h44_49.mp4 | Fixed
Replenishment request | cancel | text field | text field max character validation | 2024-04-01_03h50_41.mp4 | Fixed
Replenishment review | resend | recommended amount | recommended amount is displayed even though the request was resend | 2024-04-01_04h04_29.png | Closed
Replenishment review | resend | review form - Recommended amount | Amount is able to inter when resend request | 2024-04-01_06h32_45.mp4 | Fixed
review/approval | gl head amount | neg balance | neg balance is able to approve | 2024-04-04_08h15_31.mp4 | Fixed |  | Hoque
approval |  | available balance | agency available balance field is not showing | 2024-04-02_16h15_26.png | Fixed
Replenishment request | DRC |  | DRC user is not able to view request. DRC should be able to view list. but can not add request. DRC need to get the voucher number. so could you please block the add option for drc user and view the request list? |  | Closed
replenishment DRC | Receipt Voucher | Dark mode | table text should be in color White | 2024-04-07_08h12_40.png | Not a Defect
Replenishment request | mobile no |  | mobile no validation. is this the highest amount should be able to input? | 2024-04-08_06h22_45.mp4 | Closed
approval |  |  | when try to approve single request with 2browser, only single request is approved. but the available balance increases instead of decreasing | 2024-04-08_06h39_47.mp4 | New
|  |  |  | 2024-04-08_07h00_10.png | New
review - approval |  |  | review available balance is not not displayed correctly | 2024-04-08_07h15_17.mp4 | New
Replenishment DRC | Add new | text field | text field max character validation - 500 character is able to input in evry field | 2024-04-01_09h10_14.png | Closed
Replenishment DRC |  | Received Date | Received Date is not displayed as same as entered during Add | 2024-04-01_03h32_23.png | New
Replenishment request | edit | account type | account type is not changed after editing request | 2024-04-01_03h44_49.mp4 | Closed
Replenishment request | cancel | text field | text field max character validation | 2024-04-01_03h50_41.mp4 | Closed
Replenishment review | resend | recommended amount | recommended amount is displayed even though the request was resend | 2024-04-01_04h04_29.png | Not a Defect
Replenishment review | resend | review form - Recommended amount | Amount is able to inter when resend request | 2024-04-01_06h32_45.mp4 | Closed

## RMA
module |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
Transaction Details | notification | when change order no and doesn't match with pa no. " This Order no. doesn't match with the PA no." | 2024-04-30_16h14_58.mp4 | Fixed | Hasan
| status |  | 2024-04-30_16h14_58.mp4 | New
| Request | RMA is able to request multiple times with the Same payment advice | 2024-05-13_10h39_44.png | New | Golam
|  | is it possible to pay through Counter payment after requesting RMA? |  | need to discuss

## Payment module
module |  |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
Counter Payment | Payment Mode | Cash Warrant | Warrant No., Warrant Date should be displayed instead of Instrument No. ,Instrument Date | 2024-04-21_14h32_40.png |  | Golam |  | keep as it is
|  | Demand Draft | Demand Draft No., Demand Draft Date should be displayed instead of Instrument No., Instrument Date | 2024-04-21_14h35_30.png |  | Golam |  | keep as it is
|  |  | online fund transfer, Bank tranfer option shoyld be there? |  |  | Golam
|  | Placeholder | colleted amount | 2024-04-21_15h01_06.png | Closed | Golam
|  | Placeholder | instrument no. | 2024-04-21_15h04_26.png | Closed | Golam
Split Payment |  | Si no gl head | si no of gl head is display? or normally number should diplay? | 2024-05-05_14h52_42.png | Fixed | Golam |  | 1,2,3
2024-05-05_14h55_03.png
paid by different agency User |  | Receipt List | created PA from an agency. but counter payment was done from different agency's different user. In this situation the user who has paid is not able to see the receipt from receipt list, but able to deposit. | 2024-05-05_15h21_56.mp4 | Closed
Counter Payment | pending issue | stock | manual/ preprinted load receipt after delete/ unassign from stock |  | Closed | Hasan
Receipt Maintenance | Search Using | Receipt Type | search by receipt type is not displaying | 2024-05-09_11h44_43.png | New | Golam |  | hari sir said will discuss with client if there will be any maintenance for manual/preprinted receipt
Counter Payment | Split Payment | Duplicate Receipt | For split Payment when users submit the same payment advice simultaneously, and two different receipts are generated | 2024-05-13_13h11_50.png | New | Golam
PA Grouping | Grouping By |  | If there should be LC\Plc type ? | 2024-05-13_14h10_54.png | New
penal |  |  | penal interest gl head doesn't show in Payment receipt untill it is not selected from counter payment |  | Closed
Counter Payment | receipt Type |  | when unselect PA after choosing everything, receipt type field is automatically cleared but but page number is displayed | 2024-05-14_11h34_15.mp4 | Fixed | Golam
Receipt Maintenance | search by |  | no option search by Group Payment | 2024-05-16_14h22_43.png | New
Receipt Maintenance | PA Grouping | receipt | For group payment same receipt is displayed multiple times | 2024-05-16_14h27_21.png | New | Golam | Hoque
Deposit slip | demand draft | bank | Bank field is empty | 2024-04-21_15h58_33.png | New
Deposit slip | maintainance |  | bounced receipts are able to cancel from deposit slip maintenance | 2024-05-14_14h44_47.mp4 | New
Cheque Bounce | Search By | Filter | mendatory Field sign should be implemented | 2024-05-08_11h58_44.png | suggestion | Hasan
Cheque Bounce |  |  | Cheque details field should be displayed after clicking search option | 2024-05-08_12h03_10.png | suggestion | Hasan
reconciliation | review | back | after review accepted.. when click back button, review page is showed and again can be accepted. | 2024-05-02_14h07_16.mp4 | New | Golam
deposit slip | cancel |  | reconciliation is able to complete with cancelled deposit slip | 2024-05-05_15h32_08.mp4 | New |  | Hoque
reconciliation |  |  | bounced cheque can be reconciled |  | New |  | Hoque
reconciliation |  |  | unmapping deposit slip is possible even after reconciled deposit slip |  | New |  | Hoque
reconciliation | excel upload | date format | Currently, there is no validation for date format in Excel. When reconcile with different date format, Receipt is not genarated | 2024-05-13_15h54_32.png | New |  | Hoque
Counter Payment | Cash Denomination | Quantity | If the Quantity should be able to input more than total no | 2024-06-02_12h46_54.mp4 | Closed | Golam
Deposit Slip | Currency | decimal name | currency name for decimal is is not displayed correctly | 2024-06-02_13h23_39.png | Fixed | Golam
Panel interest | Associated Reward | Split ayment | For split payment when select GL head which doesn't have any Associated Reward is coming when do split payment |  | Fixed | Golam | Hoque
Counter Payment | Payment mode | Prepayment Deposit Adjustment | Prepayment Deposit Adjustment is not displayed when prepayment is done with the TPn |  | New | Golam
Receipt maintenance | Amend | Prepayment Deposit Adjustment | submit button shouldn't display for Prepayment Deposit Adjustment mode in receipt amend amend | 2024-06-10_16h24_48.png | New | Golam
Deposit Slip |  |  | SI no should display instead of SI | 2024-06-11_12h15_54.png | Fixed | Golam
Prepayment | Refund, Reward |  | user is able to receive a full refund of the prepayment receipt and also able to adjust payments by Prepayment Deposit Adjustment. and also able to receive a refund from the adjusted receipt |  | need to discuss
Prepayment |  |  | prepayment advice shouldn't able to group and Prepayment payment advice cannot be grouped. Also it has to be one receipt per PA |  | New | Golam
preprinted | receipt |  | when tpn is not there for the payer. their other documents (CID/ Agency code)should be displayed | 2024-06-13_15h24_25.png | New | Golam
preprinted | receipt |  | ngultrum is not displayed | 2024-06-13_15h49_33.png | New | Golam
payment | split | Receipt Date | split doesn't work when change receipt date | 2024-07-07_01h46_11.mp4 | Fixed | Golam
payment |  | notification | New Payment Advice with Bhutanese Client With Cid Details Created Successfully! |  | New |  | Hoque
money receipt |  |  | manual/ preprinted | 2024-07-07_10h52_48.png | Not a Defect
receipt | scan |  | false word display | Screenshot_2024-07-07-10-59-39-644_com.xiaomi.scanner.jpg | Closed | Golam
Deposit Slip |  |  | chetrum or chultrum |  | Fixed | Golam |  | its dynamic now
|  |  | GPA status column |  | New | Hasan

## stock
module |  |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
DRC receipt stock (preprinted) | Assigned Stock Details | List | How this manual receipt is displayed in Preprinted list. | 2024-04-05_06h36_58.png | Closed |  |  | created during deploy
Pending Issue | Counter Payment |  | manual/ preprinted load receipt and cancel at the same time |  | Fixed | Golam | Hoque
Preprinted | Surrendered Stock |  | "Preprinted Receipts are not able to surrender" instead of "Data not found.." | 2024-06-21_03h58_22.png | Not a Defect | Hasan
Canceled spelling |  |  | Canceled and Cancelled - both spelling is correct. Please make 1 spelling specific everywhere in the system |  | Fixed | Hasan | Shahin
Canceled Stock Details |  | table | Canceled From should be displayed instead of Canceled Form | 2024-06-20_10h34_49.png | Fixed | Hasan
Receipt Requisitions |  |  | When the requisition request is open & at the book is canceled. still all books are shown as approved | 2024-06-21_04h22_31.mp4 | Fixed |  | Shahin
2024-06-21_04h23_09.png
Receipt Requisitions | Fetch |  | for large amount receipt is not fetched. API time out |  | Fixed | Hasan
remarks |  |  | text length validation |  | Fixed | Hasan
Agency Receipt Stock |  | Pagination | more than 3 page is not showing |  | Fixed | Hasan
Receipt Requisitions | agency -> cancel | both manual and preprinted | Stock request for agency found - message displays when cancel request | 2024-07-06_22h57_51.mp4 | New |  | Hoque
|  | API | https://birmsstagging.drc.gov.bt/api-services/payment-service/api/v1/stock-request-agency/cancel/971
RRCO Receipt Stock | Receipt Requisitions | API | https://birmsstagging.drc.gov.bt/api-services/payment-service/api/v1/rrco-receipt-stock/delete/204 | 2024-07-07_00h40_50.mp4 | New |  | Hoque
Reason Maximum limit 250 characters
Canceled spelling |  |  | make it Canceled |  | New | Hasan
RRCO Receipt Stock-> unassign | Assign to Agencies |  | https://birmsstagging.drc.gov.bt/api-services/payment-service/api/v1/receipt-book/all/rrco-unassign?pageSize=10&pageNumber=0&receiptType=1&fromDate=&toDate=&bookNo=0 | https://drive.google.com/file/d/1tjtg07-ObktOnSs13874YJzLdnoI53Et/view?usp=drive_link | New | Hasan | Hoque
|  | create api | https://birmsstagging.drc.gov.bt/api-services/payment-service/api/v1/rrco-receipt-stock/assign-to-agency/create
accepting more than 255 charecters
Allocation To Agencies | after click save |  | during requisition if that receipt is assigned to another agency.. the field is not cleared | 2024-07-07_02h13_54.mp4 | New | Hasan

## netting off
module |  |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
Add | input field | total amount | why the total amount is not equal to input amount? | 2024-05-02_14h54_44.png | need to discuss | Golam
Add | refund amend |  | when refund is in amendment process, that receipt shouldn't show in netting off |  | New | Golam | Shahin
Add | Fetch | LC/PLC | 404 is coming when fetch LC/PLC as doc no. | 2024-06-23_17h35_10.png | New | Golam
Add | Refundable COA Details |  | after refund amend, amended GL head amount is not shown in Refundable COA Details | 2024-06-24_17h52_56.png | New | Golam | Hoque
|  |  | Total Refundable amount is not changed also | 2024-06-24_18h06_17.png

## vendor
Module |  |  | Issue | Attachment | Status | FrontEnd | BackEnd | Remarks
Vendor Registration | VIP | inactive | vendor is not able to inactive | 2024-07-04_12h50_38.png | Fixed | Hasan | Shahin

## Receipt Voucher
module |  |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
Create | Payer Identification Type : Other |  | Receipt Voucher is able to Create without selecting service and Payment Mode | 2024-07-02_14h27_01.mp4 | Fixed | Hasan
Create |  |  | When click create without selecting Payment Mode, 500 error is displayed. | 2024-07-02_14h23_27.mp4 | Fixed | Hasan
Receipt Voucher Application |  | Search by date | when input same dte in to date - from date, data is not able to find. date range issue | 2024-07-02_14h04_21.mp4 | Fixed | Hasan | Shahin
Maintenance | Payment Details |  | after decimal two digit should be displayed | 2024-07-02_15h53_22.png | Fixed | Hasan
2024-07-02_15h53_11.mp4
Maintenance |  | vendor code | vendor code is not displayed in maintenance | 2024-07-02_16h02_06.png | Fixed | Hasan
Create | Service |  | "Select major group from above" message should display | 2024-07-02_16h12_20.png | Fixed | Hasan

## Payment Voucher
module |  |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
|  |  | need to add country and currency for disbursement |  | Fixed | Golam
Health Contibution | Payment Requests | list | new request is not displayed in request list and in review list | 2024-04-29_16h54_42.mp4 | New | Golam
Health Contibution | health & other |  | not displaying in voucher maintenance list |  | New | Golam
Health Contibution | Payment Requests |  | Application, Review, and Disbursement of Health Contribution should be done from DRC. application is able to add by agency but data is showing in the DRC list |  | New | Golam
Reward |  |  | need to add country and currency for disbursement |  | New | Golam
Reward |  |  |  | 2024-04-28_07h31_33.png | New | Golam
Advance From VIP |  |  | balance |  | New |  | Hoque

## reports
module |  |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
Agency Wise COA | UI | table alignment | in pdf table, Left side has empty space. | 2024-05-05_11h19_16.png | Fixed |  | Shahin
Agency Wise COA | RRCO | Placeholder filter agency | Select agency placeholder should be displayed | 2024-05-06_12h15_39.png | Fixed | Hasan | Shahin
Agency Wise COA | DRC | Regional Office | filter Regional Office doesn't work. result is not changed when change RRCO and agency. Phuentsholing RRCO agency information is coming under Thimphu | 2024-05-06_12h44_32.mp4 | Fixed | Hasan | Shahin | getting 500 when data not fetching
2024-05-06_12h31_23.mp4
all reports filter | Excel , PDF |  | Excel and pdf is able to download in excel and pdf before view report/ generated | 2024-05-06_10h13_27.mp4 | Not a Defect
|  | filter | filter should not be able to change, when loading report. | 2024-05-05_12h35_03.mp4 | Not a Defect | Hasan |  | after click on button, the api is calling
Agency Registration | active |  | inactive status agency's are displayed as active in the report | 2024-05-05_12h27_06.png | Fixed |  | Shahin
Agency Registration | inactive |  | no data is displayed in inactive, though there are inactive data | 2024-05-05_12h35_59.png | Fixed |  | Shahin
Assigned Revenue Head Details |  | DRC | agency code is not displayed in every field. | 2024-05-05_16h25_30.mp4 | Fixed |  | Shahin | data mismatch in tbl-payment-receipt-details
Assigned Revenue Head Details | RRCO | Placeholder filter agency | Select agency placeholder should be displayed | 2024-05-08_14h14_53.png | Fixed | Hasan
|  | loader | pagination Loader need to add |  | Fixed | Hasan
| search field |  | search field is not empty when load again | 2024-05-05_17h32_03.mp4 | Not a Defect | Hasan
Agency Wise User |  | RRCO | Agency is mandatory field. but report is able to generate without selecting agency | 2024-05-06_11h37_25.mp4 | Fixed | Hasan | Shahin
Agency Wise User | RRCO | Placeholder filter agency | Select agency placeholder should be displayed. but it is displayed after selecting RRCO again | 2024-05-08_14h31_09.mp4 | Fixed | Hasan | Shahin
Agency Wise User |  | status | Removed user is displayed as active | 2024-05-06_14h34_07.png | Fixed | Hasan | Shahin
Agency Wise User | Filter | Agency Code | when Enter Agency Code before selecting agency what should happen? | 2024-05-06_14h56_47.mp4 | Fixed | Hasan
Bank Statement |  | table | Bank Statement Date and Bank Statement Amount is not showing in DRC and RRCO | 2024-05-06_16h57_07.png | need to discuss |  | Hoque
Bank Statement | Pending scenario |  | if Agency has paid split and it is deposited and reconciled RRCO is not able to see this PA. |  |  |  | Hoque | need to implement
|  |  | We can reconcile directly using PA. then this reconciled PA, RRCO/DRC is able to see. |  |  |  | Hoque
Bank Reconciliation Statement |  |  | pending
Cheque Dishonoured Statement | Filter | Placeholder | In filter Receipt Number, Instrument Number, TPN / CID / Work permit / Passport placeholder should be implemented | 2024-05-08_12h24_58.png | Fixed | Hasan
Cheque Dishonoured Statement | Filter | TPN / CID / Workpermit / Passport | there should be option to search by Document no for Organization? | 2024-05-08_14h49_33.png | need to discuss | Hasan | Hoque
Cheque Dishonoured Statement | Filter | TPN / CID / Workpermit / Passport | information is not displayed when search by TPN | 2024-05-08_15h35_06.mp4 | Not a Defect | Hasan | Hoque | TPN is for bussiness
| PDF |  | Put a dot after no(.) . Put (:) after from. RRCO is showing full form. Header : Customs | 2024-05-09_09h56_53.png | New |  | Hoque
User Application | RRCO | Placeholder filter agency | Select agency placeholder should be displayed | 2024-05-09_15h21_46.png | Fixed | Hasan

## Refund
module |  |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
|  | reason |  | 2024-04-23_10h31_30.png | Closed | Hasan
Verify Refund Application |  | Verifier remark | if possible, it would be better not to show the remark field, if the applier did not add any remark | 2024-03-13_16h40_17.png | Closed | Hasan
New Refund Application | Receipt Details | Receipt No | put a dot(.) after Receipt No |  | Closed | Hasan
Refund Application Edit | Receipt Details | Color | "Receipt Details" heading Color should be blue in the resubmit Form | 2024-04-23_12h20_16.png | Closed | Hasan
Refund Application Edit | Receipt Details | Receipt No | put a dot(.) after Receipt No | 2024-04-23_12h26_36.png | Closed | Hasan
Refund Application Edit |  | Account No | put a dot(.) after Account No | 2024-04-23_12h39_52.png | Closed | Hasan
Refund Application Edit |  | Claimant Contact Details | title name is displayed 2times | 2024-04-23_12h33_27.png | Closed | Hasan
Refund Application Edit |  |  | Placeholder missing | 2024-04-23_12h47_27.png | Closed | Hasan
Refund Application | Claimant Contact Details | Mobile No. | negative number | 2024-03-12_16h30_42.png | Closed | Hasan
Refund Application | Refund Request Details | Receipt Amount, Balance | Receipt Amount,Balance column should be right alligned | 2024-03-12_16h35_09.png | Fixed
add | UI | Receipt Details | box line should be aligned | 2024-04-28_21h49_46.png | Fixed | Hasan
amend | finter | Receipt No | put a dot(.) after Receipt No |  | Closed | Hasan
amend | Receipt Details | Color | "Receipt Details" heading Color should be blue in the resubmit Form |  | Closed | Hasan
amend |  | Receipt No | put a dot(.) after Receipt No |  | Closed | Hasan
amend |  | Account No | put a dot(.) after Account No |  | Closed | Hasan
Refund Amendment | Filter | Receipt No | put a dot(.) after Receipt No | 2024-03-13_16h46_12.png | Closed | Hasan
|  | Place holder | missing |  | Closed | Hasan
Refund Amendment | Cancel | Attach Document | new document is able to be uploaded. cancel order should be uploaded? | 2024-03-13_16h55_39.mp4 | Fixed |  | Shahin
Refund Amendment | Cancel |  | Cancelled refund is deleted from the list |  | Fixed |  | Shahin
Refund Amendment | Cancel | character limit | Reason for cancel character limit should be implemented |  | New |  | Shahin
|  |  | Email and mobile no should be able to change during amount change? | 2024-03-13_17h06_20.mp4 | Not a Defect
Verify Refund Application | Resubmitted | attachment | when add attachments in sent Back .. that attachment is not displayed in verify form | 2024-03-13_14h31_03.mp4 | Fixed |  | Shahin
Refund Application | sent Back | Reason | when sent back 2nd time, previous sent back reason is not cleared. | 2024-03-13_14h26_51.mp4 | Fixed | Hasan | Shahin
Refund Application | list | application position | application position in the list changes when edit information | 2024-03-12_16h47_07.mp4 | New |  | Shahin
Refund Application | Cancel | charecter limit | Reason for cancel character limit should be implemented | 2024-03-13_09h50_49.mp4 | Fixed |  | Shahin
Review Refund Application |  | Verifier remark | Verifier remark should be on the top of the page | 2024-03-13_15h18_14.png | New
Review Refund Application | Decision | send back | send back reason should be displayed instead of Reforward Remark | 2024-03-13_15h15_35.png | New
Verify Refund Application | Resend Reason (by Reviewer) |  | Resend Reason (by Reviewer) is not displayed | 2024-03-13_15h27_19.png | New
Verify Refund Application | Claimant | Claimant Type | Claimant type field missing | 2024-03-13_16h35_46.png | Closed
Verify Refund Application |  | Verifier remark | if possible, it would be better not to show the remark field, if the applier did not add any remark | 2024-03-13_16h40_17.png | Fixed
|  | Status | should be central aligned |  | Fixed | Hasan
referance | notification |  | message should display in the middle like reward |  | New | Hasan
|  | Edit, Resubmit | navigation | 2024-06-10_17h51_55.mp4 | Fixed | Hasan
verify | Reason for Refund | Claimant Type | nav field design is different than othr fields. and color should be lighter | 2024-06-10_17h34_55.png | Fixed | Golam
Currency |  |  | Currency Ngultrum is displayed, though currency is USD | 2024-06-11_11h41_12.png | Fixed | Hasan | Shahin | currency come from payment-receipt table
Receipt Date |  |  | receipt date is displaying the reconciled date | 2024-06-11_12h01_22.png | Closed |  | Shahin | it's ok
Status alignment |  |  | status should be middle aligned |  | Fixed | Hasan
Credit Date |  |  | Date is not implemented yet |  | need to discuss
Refund | SI |  | Sl no should display | 2024-06-11_17h22_01.png | New | Hasan
Refund Amendment |  | Assending | Request was created in last. but the request is displayed in middle. It should disply either at the top or bottom of the list | 2024-06-11_17h54_59.png | Fixed |  | Shahin
Refund Amendment Approval |  |  | Refund Amendment Approval doesn't have any user validation. Agency can also do Refund Amendment Approval | 2024-06-11_18h00_47.mp4 | Fixed | Hasan | Shahin
Verify Refund Application | Debit Bank Account Details | alignment | Debit Bank Account Details information are not aligned | 2024-06-19_16h53_22.png | New | Hasan
Remark | Placeholder |  | Add, edit, verify, Review, Resubmit, Forward, Send back | 2024-06-24_16h55_04.png | New | Hasan
Amend | Reason | Placeholder |  | 2024-06-24_17h06_14.png | New | Hasan

## Disbursement
module |  |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
Disbursement Voucher | table | Reference No. | Reference No. is changed when approved | 2024-04-03_06h49_05.png | Closed
initiate Disbursement | table | column name | column name should be left aligned. table column name alignment should be unified | 2024-04-03_07h19_44.png | Fixed | Hasan | Shahin
Generate Disbursement Voucher | table | Approval Date | approval date is displayed Payment Voucher Date | 2024-04-08_07h33_40.png | Closed
Generate Disbursement Voucher | filtered |  | Deleted Data is displayed | 2024-04-08_07h50_58.mp4 | Fixed |  | Shahin
Generate Disbursement Voucher | edit | RPV240408500827 | 2 gl head is displayed when edit. but table information displayed correctly when add | 2024-04-08_08h11_47.png | Closed |  |  | not getting date like this
|  |  |  | 2024-04-08_08h25_55.mp4 | Closed
Generate Disbursement Voucher | notification | Edit |  |  | New
voucher |  |  | No. | 2024-04-08_09h21_21.png | Fixed
Disbursement Voucher Approve |  |  | cancelled by Disbursement Voucher maintenance, after that when add again threshold is not able to input more than the amount. and pending application is not able to approve. |  | Closed
| 400 error | API | https://birmsstagging.drc.gov.bt/api-services/payment-service/api/v1/disbursement-voucher/approved/301?approvedRemarks=&approvedReason=&decision=211 | 2024-04-09_08h16_17.mp4 | Fixed | Hasan | Shahin
Generate Disbursement Voucher | Currency |  | when Generate Disbursement Voucher the currency drop-down is not able to fetch the other currency's. As after reconciliation the currency converts into ngultrum. |  | New | Hasan | Shahin
pdf download |  |  | full page is not displayed | Disbursement Voucher (4).pdf | New | Hasan
Generate Disbursement Voucher | Details |  | Details field is not implemented | 2024-06-30_16h50_39.png | Fixed | Hasan | Shahin
Generate Disbursement Voucher | Currency |  | For other currency, decimal currency name is showing chultrum every time | 2024-06-30_16h51_09.png | New | Hasan
Generate Disbursement Voucher | Currency Symbol |  | Currency Symbol is not showing | 2024-06-30_16h51_09 (1).png | New | Hasan
Generate Disbursement Voucher | table | Alignment | amount name should be middle align | 2024-06-30_17h27_58.png | New | Hasan
Reward before deposit |  | invalid date | Disbursement Voucher Date is shown invalid for reward before deposit | 2024-07-08_17h20_37.png | New | Hasan

## AUDIT MANAGEMENT
module |  |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
Action To Be Taken | Responses and Recoveries |  | If possible make Response table smaller. and reduce the gap between the tables | 2024-04-24_16h08_55.png | suggestion
| Edit | Title | Edit should be displayed | 2024-04-24_16h39_15.png | New
| Forward Details | Alignment | Forward Details information should be aligned with title | 2024-04-24_16h42_28.png | New
Audit Plans | breadcrums |  |  | 2024-04-13_11h09_23.png | New
Audit Plans | Add | user | no option to add user |  | Not a Defect |  |  | option only for agency
Audit Plans | Add | user |  | 2024-04-14_07h34_01.png | New
Audit Response |  |  | Date format | 2024-04-14_16h13_14.png | New | Hasan
Audit Response |  | breadcrums |  | 2024-04-14_23h29_22.png | New | Hasan
Audit Plans | New Action To Be Taken | Place holder |  | 2024-04-15_05h58_35.png | New
Audit Plans | Edit |  | button name should be Update instead of save | 2024-04-26_17h55_08.png | suggestion
Revenue Audit Report | report |  | middle align | 2024-04-28_00h50_40.png | suggestion
new New Response | New Action To Be Taken | Placeholder | CID | 2024-04-28_01h11_15.png | New
new New Response | New Action To Be Taken | CID validation | CID number can be changed after fetch name by CID and invalid number can be input | 2024-04-28_01h20_43.mp4 | New
new New Response | New Action To Be Taken | Recovery Amount | neg number is able to input | 2024-04-28_01h25_01.mp4 | New
new New Response | New Action To Be Taken |  | not able to add | 2024-04-28_01h38_41.mp4 | New

## ARREAR MANAGEMENT
module |  |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
| Notification Configuration | Add | neg days are able to input | 2024-04-28_14h34_10.mp4 | Fixed | Hasan
2024-04-28_14h34_28.png
| Aging Report | view | option is able to change after click view option | 2024-04-28_15h40_26.mp4 | Fixed | Hasan

## Revenue Forecast
module |  | issue | Attachment | Status | FrontEnd | BackEnd | Remarks
Previous Year Revenue | Collection Amount | max 2 number after decimal should be displayed | 2024-04-16_13h25_45.png | New
| Update Collection | Review | 2024-04-16_15h52_58.png | New
maintainance | title | maintainance | 2024-04-18_13h13_42.png | New
maintainance | reason | maintenance field should be mandatory? | 2024-05-21_15h27_52.png | need to discuss
| Resubmit Collection | max 2 after decimal number | 2024-05-21_15h56_58.png