## Receipt Stock
module | Issues | status | frontend | backend | Remark
Agency Receipt Stock-> Receipt Stock-> Assigned On | date is not displayed for new added stock |  | done | Shahin
Agency Receipt Stock -> Receipt Requisitions -> add | when add preprinted, then click edit to check, it displays manual |  |  | Shahin
Agency Receipt Stock -> Receipt Requisitions -> edit | when edit manual to preprinted doesn't work |  |  | Shahin
Agency Receipt Stock-> Receipt Stock-> Assigned On | Agency-> Assigned on date is not displayed
RRCO-> New Receipt Requisition-> Preprinted Receipt | Number of Books are being able to selected instead of receipt numbers. for RRCO user
ReAssigned Stock- Balance -> Balance is displayed as zero
| assigned on date is displayed 09-12-2023 instead of10\23\23 |  |  | hasib
DRC -> To Book No. fields | To Book No. field duplicate checks before From Book No. | Done |  | Shahin
DRC-> add-> New Recipt Number Creation | Recipt -> Receipt spelling mistake | Done | Hasan | shahin
DRC-> Surrender stock Details | Surrendered Stock Details should be displayed |  | Hasan | shahin
DRC-> Cancel -> Heading | Assign Stock to RRCO is displayed in the title instead of Cancel Stock |  | Hasan | shahin
Assigned Stock Details->cancel-> unassign->unassign | title - Reassign Stock to RRCO |  | Hasan | shahin
Cancel | Select Book -> Data not found... message displays | done |  | shahin
DRC-> New Receipt Number Creation-> Manual | From Book No. set fix
Allocation TO RRCO | Allocation TO RRCO -> Receipt Allocation TO RRCO's | fixed
Allocation TO RRCO-> Review | allocate button is not working | fixed
Allocation TO RRCO-> Review-> title | Review RRCO Stock Requisition Allocation-> Review Receipt Requisition Allocation to RRCO
RRCO Receipt Stock-> Assigned -> Cancel : | Receipts are not loading
Remarks | text max character is not defined
manual receipt -> reassign ->surrender | when already used a book, reassign buttons should be blocked
User-> change agency-> assign agency by RRCO | when user changes agency, that changed information is not updated in Assign to Agencies by RRCO -> Select User : user name is not found
Agency-> Assigned | Assigned on date is not displayed
DRC -> Surrender -> manual | page is not loading | Fixed
surrender notification | Book is surrendered\ Books are surrendered | Fixed
DRC -> Reassign | for used receipts, Reassign shouldn't be possible. Unassign is possible but then again it can't be assigned.
RRCO Receipt Requisitions | column should be added - Allocated number of receipts
RRco Reassign -> used receipts | Only for user should possible
RRCO Receipt Requisitions | used receipt -> shouldn't be able to allocate other agency

## Refund
module | Issues | status | frontend | backend | Remarks
Refund Application | review doesn't work for group payment reciept | Fixed |  | Shahin
attachment is not able to download from review or edit
| Receipt Amount, Balance, and Refund Amount text should be right alignment |  | hasan
| edit option is not working not working | Fixed |  | Shahin
| though the full receipt was not refund, still it is not able to add 2nd time | Fixed |  | Shahin
| when image is uploaded in the attachment, file is not able to save | Fixed |  | Shahin
| RRCO-> Verify Refund Application-> review is not working | Fixed |  | Shahin
| RRCO-> Verify Refund Application-> date filter is not working | Fixed |  | Shahin
| available balance is not updated\adjusted when application get rejected by RRCO\DRC | Fixed |  | Shahin
| neg Balance is displayed for multiple PA\GPA | Fixed |  | Shahin
ReAssigned Stock- Balance -> Balance is displayed as zero
| mobile spelling mistake | Fixed | Hasan
alignment | Receipt Amount, Balance, and Refund Amount text should be right alignment | Fixed
Add | multiple PA\GPA edit option is not working not working | fixed
| Receipt does not display | fixed
Edit | though the full receipt was not refund, still it is not able to add 2nd time for multiple PA\GPA | fixed
Add | though the full receipt was not refund, still it is not able to add 2nd time for multiple PA\GPA
Add-> Claimant Type | Placeholder : Select Claimant Type |  | Hasan
Attach Document | Attach Document is not able to download
RRCO-> Verify Refund Application-> Table | ReceiptDate -> Space should be in between ReceiptDate. |  | Hasan
RRCO-> Verify Refund Application-> search filter | Search by reference no is not working, without selecting date
RRCO-> Verify Refund Application-> Date search filter | Date field is mandatory when it is clear

## RMA
module | Issues | status | frontend | backend | Remarks
RMA Failed Transactions Review-> Filter | Filter not working
Penal interest | After RMA Failed Transactions Review amount is shows with penal interest
RMA Failed Transactions-> Receipt | Approved Transactions Receipt is not able to view

## Advanced Payment
module | Issues | status | frontend | backend | Remarks
Review | Attached Document is missing: view\download |  |  | Shahin
Review | The field name should be Remarks instead of Reason
Review -> Payment Details | Mode of Payment should be displayed instead of Payment Mode
Add | GL head is not Mapped

## Reward
module | Issues | status | frontend | backend | Remark
Reward Before Deposit-> New Reward Request | Only 1gl head value is displayed instead of all values

## MIS Report
module |  | Issues | status | frontend | backend | Remark
Ledger-> report | Title | Collection Report displays instead of ledger
breadcrum
Receipts Deposit Statement Report | Filter | Major group not working | Fixed |  | Hoque
Cash Book |  | numbers were not displayed properly for split payment

## others
module | issue | Status | FrontEnd | BackEnd
Receipt List | more than 20 receipt list is not displayed when searching by date
payment-> receipt | Auto payment is generated when waiting for RRCO to assign a manual stock receipt. but no payment receipt is generated.
reconciliation | notification spelling
numbers were changed for large amounts when reconciliation review
1 of the DS was not reconciled when rejected by review and then accepted
Deposit Date | it shows the previous date,
Reconciliation | Bank Journal No. -> decimal number displayed
Reconciliation Date & Statement Date is different. though worked on the same day
Receipts for Deposit Statement | Deposit Slip Amount & Bank Statement Amount is different
Payment Requests | 404 Error page
Receipt maintenance, Receipt List-> Reprint: | split payment receipt is not showing correct value when reprint.
Counter Payment-> Reissue Receipt | Bounced Reiepts should also be able to Reissue. As Bounced is also reversed receipt.
Payment -> view | bank details should't come | Fixed
Time | Stagging is 6hr slower than local time
Payment Receipt maintenance | 1 receipt displays 3times | Fixed
Receipt Maintenance-> Revarsal | reversal not working
Recieipt list->amount | should be right align
amend ->QR | false total amount displayed
Receipt List-> GP no | search by gp doesn't work

## Logic
Group Payment | Counter Payment | CID/tpn search doesn't display GPA
Update Refund Application: |  | Edit Reason field is in moc up but not in system.
RMA QR Code |  | not implemented in the system. as it is in moc up | https://drive.google.com/file/d/1a0A5NVYfaMa_PkeRpy0V9p25RlvoBw3Y/view?usp=drive_link
Do we need to send any message in mail, when unmap receipt from receipt maintenance?
Stock |  | Only unused recepts can be surrendered. If from a book some receipts are used then remaining can be surrendered.
manual receipt if some are used from the book then cannot be reassigned. But for pre-printed receipts even if some are used from a book ... unused can be reassigned. The logic is for manual receipt a book will have 100 receipts whereas for pre-printed 100 receipts will make one book.
when surrendered than it will be unassigned. But if manual receipt and some are used then it cannot be assigned to another agency but can be reassigned to different user of the same agency.
| Surrender | Pre-printed can't be surrendered. manual unused won't be surrendered. when used are surrendered, rest will be cancelled
Group payment -> Receipt maintenance unmap issue -> pending
Refund ->Amend | User can't amend if it's Disbursed
Refund | Zero is not able to input

## note
Refund :
| Agency : add Refund | input number field | user is not able to add zero input.
RMA
| ADD-> Filter | Transaction No. | not in system. Difference from mock up
Replenishment
| Filter |  | If there should be any filter for search by Reference No.