## Sheet1
Assigned Task | FrontEnd | BackEnd | Status | Remarks | 2024-01-10 | 2024-01-11 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-23 | 2024-01-24
REPORT
Demand And Collection Register report | Hasibul Hasan | Hasibul Hoque |  | need to discuss | 2024-01-10: Primarily completed. Waiting for a logic confirmation
All Agencies Consolidated Bank Ledger | Hasibul Hasan
Bank Reconciliation Statement | Hasibul Hasan
Consolidated Bank Ledger | Hasibul Hasan | Hasibul Hoque |  |  | 2024-01-10: Complete
User Role List | Hasibul Hasan | Shahin |  |  | 2024-01-10: On-Process; 2024-01-11: Complete
Receipt Reversal Statement | Hasibul Hasan | Hasibul Hoque |  |  | 2024-01-11: On-Process; 2024-01-14: Complete
Agency Wise User | Hasibul Hasan | Shahin |  |  | 2024-01-10: On-Process; 2024-01-11: Complete
User Status | Hasibul Hasan | Shahin |  |  | 2024-01-11: On-Process; 2024-01-14: Complete
Agency Registration Report | Hasibul Hasan | Shahin |  |  | 2024-01-14: On-Process; 2024-01-15: On-Process; 2024-01-16: Complete
On-Process
Consolidated Bank Ledger Jasper Report | Hasibul Hasan | Hasibul Hoque |  |  | 2024-01-14: Complete
Receipt Reversal Statement Jasper Report | Hasibul Hasan | Hasibul Hoque |  |  | 2024-01-15: Complete
User Application | Hasibul Hasan | Shahin
Demand And Collection Register Jasper report | Hasibul Hasan | Hasibul Hoque |  |  | 2024-01-15: On-Process; 2024-01-16: Complete
Ledger Jasper report | Hasibul Hasan | Hasibul Hoque |  |  | 2024-01-15: On-Process; 2024-01-16: Complete
Deposit Details Jasper report | Hasibul Hasan | Hasibul Hoque |  |  | 2024-01-15: On-Process; 2024-01-16: On-Process; 2024-01-17: Complete
Assgined Revenue GL Head Details | Hasibul Hasan | Shahin |  |  | 2024-01-15: On-Process; 2024-01-16: On-Process; 2024-01-17: Complete
Requirements collected for new Reports |  | Hasibul Hoque |  |  | 2024-01-17: Complete
Bug Fixes previous report |  | Hasibul Hoque |  |  | 2024-01-17: Complete
Cheque Dishonoured Statement with Excel Datasheet and Jasper Pdf download | Hasibul Hasan | Hasibul Hoque |  |  | 2024-01-18: Complete
Prepayment Deposit Statement full report complete with Excel and Jasper Report | Hasibul Hasan | Hasibul Hoque |  |  | 2024-01-18: Complete
Prepayment Deposit Adjustment Statement full report complete with Excel and Jasper Report | Hasibul Hasan | Hasibul Hoque |  |  | 2024-01-23: Complete
ScheduleOfCollectionDeposit jasper report completed | Hasibul Hasan | Hasibul Hoque |  |  | 2024-01-24: Complete
RISK MANAGEMENT
Risk Profile Entity | Golam / Hasan | Hoque | Completed |  | 2024-01-10: 2024-01-09
Risk Actions | Golam / Hasan | Faisal | Backend pending |  | 2024-01-10: 2024-01-10; 2024-01-11: 2024-01-11
Risk Transaction / Process | Golam / Hasan | Faisal | Backend pending |  | 2024-01-10: 2024-01-10; 2024-01-11: 2024-01-11
Risk Levels | Golam / Hasan | Faisal | Backend pending |  | 2024-01-10: 2024-01-10; 2024-01-11: 2024-01-11
Risk Parameters / Indicators | Golam | Faisal | Backend pending |  | 2024-01-10: 2024-01-10; 2024-01-11: 2024-01-11
Risk Areas | Golam | Faisal | On process
Risk Level Threshold | Golam | Faisal | On process
Receipt Stock
Receipt Digit for Manual and Preprinted | Hasibul Hasan | Shahin | done |  | 2024-01-10: 2024-01-10; 2024-01-11: 2024-01-11
RRCO Agency user filter bug fix |  | Hasibul Haque |  |  | 2024-01-11: 2024-01-11
Bug Fix | Hasibul Hasan & Goalm | Hasibul Haque & Shahin |  |  | 2024-01-14: Complete
Bug Fix | Hasibul Hasan & Goalm (Kichu kore nai) | Hasibul Haque |  |  | 2024-01-15: Complete
Stock : Book no., Reassign | Golam | Shahin | done |  | 2024-01-10: 2024-01-10
Advance Payment | Golam | Shahin | done |  | 2024-01-10: 2024-01-10
Reward before deposit | Golam | Shahin | done |  | 2024-01-10: 2024-01-10
Fixed receipt type changing to manual when tab is changed | Golam |  |  |  | 2024-01-11: 2024-01-11
Fixed rrco-receipt-stock canceled page list not updating | Golam |  |  |  | 2024-01-11: 2024-01-11
Fixed drc and rrco receipt-stock cancel without selecting page | Golam |  |  |  | 2024-01-11: 2024-01-11
Fixed drc assign not working | Golam |  |  |  | 2024-01-11: 2024-01-11
Fixed manual book validation problem resolved | Hasibul Hasan | shahin |  |  | 2024-01-14: Complete
Bug Fixed RRCO receipt stock unassaign | Hasibul Hasan & Goalm | Hasibul Hoque |  |  | 2024-01-14: Complete
Bug Fixed DRC receipt stock unassaign | Hasibul Hasan & Goalm | Hasibul Hoque |  |  | 2024-01-14: Complete
Date: 23/01/2024
Reconciliation Receipt date issue fixed as per requirement |  | Hasibul Hoque |  | Reconciliation Service Impl, Payment Receipt Details entity class will go in production | bar: 2024-01-14
Date: 24/01/2024
Reconciliation Receipt duplicate issue fixed as per requirement |  | Hasibul Hoque |  | Reconciliation excel data entity class will go production | bar: 2024-01-14
Counter payment receipt created date not savig issue |  | Hasibul Hoque |  | Payment Ledger service impl create will go production
Reward Payment before deposit slip create issue resolved |  | Hasibul Hoque